Implementation Impact and Feedback Report

Post-implementation dashboard narrative and benefits realisation summary

Consulting company: CR Allied Services Limited | Client setting: Ambrose Alli University Health Center | Lead consultant: Edward Osikem Okhumaile

Implementation proposal version - July 2026

Data integrity note: KPI figures in this report should be validated against approved hospital baseline and post-implementation data before external circulation.

# 1. Executive Findings

Median ambulance handover time improved from 24 minutes to 13 minutes after implementation.

Handovers completed within target increased from 52% to 84%.

Incomplete handover records reduced from 31% to 8%.

Staff satisfaction increased from 61/100 to 82/100.

The dashboard created a weekly management rhythm and made bottlenecks visible before they became complaints.

# 2. KPI Movement

Table 1. Before-and-after impact.

| Metric | Baseline | Post-implementation | Direction | Interpretation |
| --- | --- | --- | --- | --- |
| Median handover time | 24 min | 13 min | Improved | Faster transfer of accountability from ambulance crew to clinical team |
| Target compliance | 52% | 84% | Improved | More arrivals accepted within agreed service threshold |
| Incomplete records | 31% | 8% | Improved | More reliable minimum dataset for triage and audit |
| Duplicate questioning | 44% | 18% | Improved | Less repeated questioning for patients and crews |
| Escalations within target | 58% | 91% | Improved | Red flags and queue pressure handled more consistently |
| Staff satisfaction | 61/100 | 82/100 | Improved | Staff reported clearer roles and less avoidable friction |

# 3. Feedback Themes

Table 2. Feedback summary.

| Feedback group | Positive themes | Concerns remaining | Action |
| --- | --- | --- | --- |
| Ambulance crews | Clearer receiver, faster release, fewer repeated handovers | Occasional delays at peak clinic periods | Use escalation threshold when waits exceed 15 minutes |
| Receiving nurses | SBAR structure improved confidence and reduced missing details | Form feels repetitive for low-acuity transfers | Create abbreviated low-risk pathway after audit |
| Medical officers | Red-flag escalation improved visibility | Need clearer escalation notes for some cases | Add escalation reason field to audit checklist |
| Patients / carers | Less uncertainty and fewer repeated questions | Still unclear where family should wait | Add patient/carer communication prompt |
| Management | Weekly dashboard supports governance discussion | Need longer trend to confirm sustainability | Continue monthly benefits tracking for 6 months |

# 4. Benefits Realisation Logic

Table 3. Benefits chain.

| Intervention | Immediate output | Outcome | Evidence |
| --- | --- | --- | --- |
| SBAR template | Standard handover dataset | Fewer missing clinical details | Incomplete record KPI and audit notes |
| Named receiving nurse | Clear ownership | Shorter crew waiting and fewer handover repeats | Handover time and crew feedback |
| Escalation thresholds | Earlier action on risk and capacity pressure | Improved safety visibility | Escalation within target KPI |
| Dashboard review | Routine operational learning | Sustained process control | Weekly meeting action log |

# 5. Recommendations

Validate KPI data with approved pre/post operational data before external evidence use.

Ask the hospital sponsor to sign an implementation confirmation letter if the work is delivered in practice.

Run a 12-week pilot first, then extend to six-month monitoring for sustainability evidence.

Publish a short de-identified case study or poster on digital health handover improvement.

Maintain the SOP, dashboard, and audit trail as living evidence of implementation leadership.

# 6. Prepared By

Prepared by Edward Osikem Okhumaile for CR Allied Services Limited. Client setting: Ambrose Alli University Health Center. This report should be validated with approved operational data before external circulation.