Business Requirements Document

Ambulance handover operating model and dashboard requirements

Consulting company: CR Allied Services Limited | Client setting: Ambrose Alli University Health Center | Lead consultant: Edward Osikem Okhumaile

Implementation proposal version - July 2026

Scope assumption: The BRD is written for a small-to-medium hospital health centre context and can be adapted to local clinical governance, regulatory, and IT policies.

# 1. Objectives

Reduce ambulance-to-clinical handover delay and make waiting time visible.

Standardise the minimum clinical and operational information captured at handover.

Clarify roles and escalation rules during routine and peak periods.

Create auditable records for quality improvement and operational performance review.

Improve patient and staff experience by reducing repeated questions and uncertainty.

# 2. Scope

Table 1. Scope definition.

| In scope | Out of scope |
| --- | --- |
| Ambulance arrival logging, SBAR handover form, escalation thresholds, dashboard KPIs, SOP, training, feedback capture | Ambulance dispatch system replacement, full electronic medical record implementation, procurement of ambulance vehicles, clinical treatment protocol redesign |

# 3. Functional Requirements

Table 2. Functional requirements.

| ID | Requirement | Priority | Acceptance criteria |
| --- | --- | --- | --- |
| FR-01 | Record ambulance arrival date/time, crew ID, patient identifier, presenting complaint, and receiving nurse. | Must | Every ambulance arrival has a timestamped log entry. |
| FR-02 | Capture SBAR handover fields using a standard template. | Must | Template includes Situation, Background, Assessment, Recommendation, allergies, medication, vitals, and red flags. |
| FR-03 | Trigger escalation when red flags or waiting thresholds are met. | Must | Escalation reason, time, and notified clinician are recorded. |
| FR-04 | Provide weekly KPI dashboard for leadership review. | Must | Dashboard shows median handover time, target compliance, incomplete records, escalations, and feedback. |
| FR-05 | Capture staff and patient/carer feedback after implementation. | Should | Monthly feedback summary includes theme, sentiment, and action owner. |
| FR-06 | Maintain audit trail of handover corrections. | Should | Corrected entries preserve original value, reason, date, and correcting user. |

# 4. Non-Functional Requirements

Table 3. Non-functional requirements.

| Category | Requirement | Measure |
| --- | --- | --- |
| Usability | Handover form must be usable during urgent, high-pressure arrival conditions. | Core fields completed within 8 minutes. |
| Availability | Paper fallback must exist if digital form is unavailable. | Fallback pack stocked and checked each shift. |
| Privacy | Patient-identifiable information must be handled under hospital privacy rules. | Access limited to authorised clinical/operations staff. |
| Reporting | KPIs must be understandable to clinical and non-clinical managers. | Dashboard includes definitions and traffic-light thresholds. |
| Training | Staff must receive short role-based training before go-live. | At least 90% of target staff trained. |

# 5. Traceability Matrix

Table 4. Requirement-to-benefit traceability.

| Requirement | Linked benefit | KPI |
| --- | --- | --- |
| FR-01 Arrival log | Improved visibility and queue control | Arrivals logged within 1 minute |
| FR-02 SBAR template | Reduced missing information | Incomplete handover rate |
| FR-03 Escalation trigger | Faster response to clinical risk | Escalations documented within target |
| FR-04 Dashboard | Sustained management oversight | Weekly KPI review completed |
| FR-05 Feedback | Adoption and experience improvement | Staff satisfaction and patient/carer feedback |

# 6. Key Risks and Controls

Table 5. Risk register summary.

| Risk | Impact | Control |
| --- | --- | --- |
| Staff bypass the form during peak pressure | Incomplete data and inconsistent handover | Keep form short, assign receiving nurse, audit weekly exceptions |
| Clinicians perceive dashboard as punitive | Low adoption | Frame KPIs as service improvement and show team-level trends |
| Digital access unavailable | Process interruption | Maintain paper fallback and retrospective entry rule |
| Feedback data is biased | Misleading benefits report | Collect feedback from crews, nurses, clinicians, and patients/carers |