Stakeholder Team Meeting Transcript

Discovery meeting that initiated the Ambulance Handover Process Improvement project

Consulting company: CR Allied Services Limited | Client setting: Ambrose Alli University Health Center | Lead consultant: Edward Osikem Okhumaile

Implementation proposal version - July 2026

Evidence integrity note: This stakeholder record should be verified against approved meeting minutes and project communication records before external circulation.

# 1. Meeting Overview

Table 1. Meeting metadata.

| Item | Details |
| --- | --- |
| Meeting title | Ambulance Handover Process Improvement - Stakeholder Discovery |
| Date / time | 8 July 2026, 09:00-09:45 |
| Facilitator | Edward Osikem Okhumaile, Business Analyst, CR Allied Services Limited |
| Client setting | Ambrose Alli University Health Center |
| Purpose | Agree the operational problem, capture stakeholder pain points, define project scope, and confirm pilot deliverables. |
| Meeting outcome | Stakeholders agreed to proceed with a 12-week pilot supported by BRD, SOP, RACI, escalation rules, audit form, and KPI dashboard. |

# 2. Attendees and Roles

Table 2. Stakeholder attendees.

| Name | Role | Contribution |
| --- | --- | --- |
| Dr. Miriam Aigbe | Medical Officer / Clinical Lead | Clinical risk, red-flag escalation, urgent decision making |
| Nurse Grace Okon | Triage Nurse Lead | Triage workflow, handover completeness, nursing adoption |
| Mr. Paul Ekhator | Ambulance Liaison Officer | Crew waiting time, repeated handover, ambulance release |
| Mrs. Ifeoma Nwosu | Operations Manager | Operational ownership, pilot approval, management reporting |
| Mr. Tunde Bello | Quality and Patient Safety Officer | Audit, safety evidence, governance review |
| Ms. Amaka Obi | Health Records / Data Analyst | Dashboard data fields and reporting definitions |
| Mrs. Helen Musa | Patient Services Representative | Patient/carer experience and communication |
| Edward Osikem Okhumaile | Business Analyst | Facilitated discovery, documented requirements, translated issues into project artefacts |

# 3. Meeting Transcript

Table 3. Transcript extract - opening problem definition.

| Time | Speaker | Transcript |
| --- | --- | --- |
| 9:02 AM | Mrs. Ifeoma Nwosu | Good morning everyone. Thank you for joining. We need to agree whether the ambulance handover delays are a process problem, a staffing problem, or both. |
| 9:03 AM | Edward Osikem Okhumaile | Thanks. I will facilitate today as discovery. I am listening for pain points, decision rules, missing data, and where ownership becomes unclear. |
| 9:05 AM | Mr. Paul Ekhator | From the ambulance side, the biggest issue is not knowing who is formally receiving the patient. Sometimes crews repeat the same handover to two or three people. |
| 9:06 AM | Nurse Grace Okon | That happens because triage is also trying to identify risk quickly. If the first handover is incomplete, we ask again to protect the patient. |
| 9:08 AM | Dr. Miriam Aigbe | The clinical risk is missing red flags. We need a short SBAR structure, not a long form that delays urgent cases. |
| 9:10 AM | Edward Osikem Okhumaile | So I am hearing: named receiver, short SBAR minimum dataset, red-flag escalation, and a single timestamped log. Is that a fair starting point? |
| 9:11 AM | Mr. Tunde Bello | Yes. And we need a weekly audit. At the moment we only hear about delays when there is a complaint. |

Table 4. Transcript extract - requirements and patient experience.

| Time | Speaker | Transcript |
| --- | --- | --- |
| 9:18 AM | Ms. Amaka Obi | For dashboard reporting, we can capture arrival time, handover start, handover end, receiver, escalation reason, and whether the SBAR fields were complete. |
| 9:20 AM | Mrs. Helen Musa | Patients and relatives mainly complain about uncertainty. They do not know whether they have been accepted or are still waiting for handover. |
| 9:22 AM | Nurse Grace Okon | A patient communication prompt would help. Once handover is complete, someone should explain the next step to relatives if appropriate. |
| 9:24 AM | Edward Osikem Okhumaile | I will add that to the future-state process: clinical acceptance plus patient/carer communication prompt. It supports experience as well as safety. |
| 9:26 AM | Mrs. Ifeoma Nwosu | Can we pilot this for 12 weeks before making it permanent? I want data before we ask for wider changes. |
| 9:27 AM | Edward Osikem Okhumaile | Agreed. I will produce the BRD, SOP, RACI, escalation rules, audit form, and dashboard structure for pilot approval. |
| 9:29 AM | Dr. Miriam Aigbe | Please make sure the SOP says this supports clinical judgement. It must not replace urgent clinical decisions. |

Table 5. Transcript extract - pilot decision and actions.

| Time | Speaker | Transcript |
| --- | --- | --- |
| 9:34 AM | Mr. Tunde Bello | Decision summary: we proceed with a pilot. Success measures should include median handover time, incomplete records, duplicate questioning, escalation within target, and satisfaction. |
| 9:35 AM | Mr. Paul Ekhator | Please include ambulance crew release time. If we reduce repeated handovers, crews can return to service sooner. |
| 9:37 AM | Nurse Grace Okon | Training must be short. Staff will not attend a half-day session for a form. |
| 9:38 AM | Edward Osikem Okhumaile | Noted. I will propose role-based 30-45 minute sessions and a one-page checklist for shift use. |
| 9:40 AM | Ms. Amaka Obi | I can help validate the data fields and dashboard definitions. |
| 9:42 AM | Mrs. Ifeoma Nwosu | Good. Edward, please circulate the process map and requirements by Friday. We will review next week. |
| 9:43 AM | Edward Osikem Okhumaile | Thank you. I will circulate the project artefacts with assumptions, open questions, and the pilot evidence plan. |

# 4. Decisions and Actions

Table 6. Decision and action log.

| Decision / action | Owner | Due | Evidence output |
| --- | --- | --- | --- |
| Proceed with ambulance handover pilot | Operations Manager | Next governance meeting | Implementation proposal index and case study |
| Create SBAR handover minimum dataset | Edward Osikem Okhumaile | Friday after meeting | BRD and SOP toolkit |
| Define red-flag and waiting-time escalation thresholds | Clinical Lead + Business Analyst | Pilot design review | SOP escalation section |
| Confirm dashboard data fields and KPI definitions | Data Analyst + Business Analyst | Before pilot launch | Impact dashboard workbook |
| Prepare staff training approach | Triage Lead + Quality Officer | Go-live readiness | Training plan and audit form |
| Review patient/carer communication prompt | Patient Services Representative | SOP review | SOP and feedback report |

# 5. Teams Conversation Screenshots

The screenshots below summarise stakeholder alignment, decision-making, and business analysis facilitation for the project record.

Figure 1. Teams conversation screenshot 1.

Figure 2. Teams conversation screenshot 2.

Figure 3. Teams conversation screenshot 3.